## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project orientation and environment setup | MUST HAVE | No | Prem Chavan | 3- Completed
S1 | S1 | US-001 | Load and inspect CSV data files | MUST HAVE | CSV Data files | Prem Chavan | 3- Completed
S1 | S1 | US-001 | Data preprocessing – handle missing values and duplicates | MUST HAVE | CSV Data files | Prem Chavan | 3- Completed
S1 | S1 | US-001 | Merge multiple CSV sources into unified dataset | MUST HAVE | CSV Data files | Prem Chavan | 3- Completed
S2 | S2 | US-001 | Learning about Neo4j | MUST HAVE | NO | Prem Chavan | 3- Completed
S2 | S2 | US-001 | Inserting the Data in to Neo4j Aura | MUST HAVE | Clean CSV Data | Prem Chavan | 3- Completed
S2 | S2 | US-001 | Building Knowledge Graphs | MUST HAVE | Clean CSV Data | Prem Chavan | 3- Completed
S3 | S3 | US-001 | Integrate Groq/Llama LLM API for entity extraction | MUST HAVE | Groq API Key | Prem Chavan | 3- Completed
S3 | S3 | US-001 | NER and relationship extraction | MUST HAVE | LLM API | Prem Chavan | 3- Completed
S3 | S3 | US-001 | Store knowledge graph data in Neo4j Aura | MUST HAVE | Neo4j Aura Instance | Prem Chavan | 3- Completed
S3 | S3 | US-001 | Generate text embeddings using SentenceTransformers | MUST HAVE | NO | Prem Chavan | 3- Completed
S3 | S3 | US-001 | Build and index FAISS vector store | MUST HAVE | Embeddings | Prem Chavan | 3- Completed
S3 | S3 | US-001 | Build hybrid search combining semantic + keyword results | MUST HAVE | Text | Prem Chavan | 3- Completed
S4 | S4 | US-001 | Work with streamlit | MUST HAVE | streamlit | Prem Chavan | 3- Completed
Note on F1: ====== ID#AAAB0aYi-Z8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 29 | 12 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to Project | 2026-02-02 | 2026-02-02 | Prem Chavan | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Working with Data | 2026-02-03 | 2026-02-04 | Prem Chavan | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Data preprocessing – handle missing values and duplicates | 2026-02-05 | 2026-02-06 | Prem Chavan | Coding | 3- Completed | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Merge multiple CSV sources into unified dataset | 2026-02-06 | 2026-02-06 | Prem Chavan | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Learning about Neo4j | 2026-02-09 | 2026-02-11 | Prem Chavan | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Inserting the Data in to Neo4j Aura | 2026-02-16 | 2026-02-18 | Prem Chavan | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Building Knowledge Graphs and Testing | 2026-02-17 | 2026-02-19 | Prem Chavan | Unit Test | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Integrate Groq/Llama LLM API for entity extraction | 2026-02-17 | 2026-02-18 | Prem Chavan | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Build and index FAISS vector store | 2026-03-03 | 2026-03-23 | Prem Chavan | Coding | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Testing | 2026-03-17 | 2026-03-20 | Prem Chavan | System Test | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 11 | Using streamlit | 2026-03-23 | 2026-02-27 | Prem Chavan | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 12 | Documentation | 2026-03-25 | 2026-03-27 | Prem Chavan | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAAB0aYi-ZM Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAAB0aYi-aE Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on J3: ====== ID#AAAB0aYi-Zc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAAB0aYi-Zk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAAB0aYi-aM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAAB0aYi-ZU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAAB0aYi-ZQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAAB0aYi-Z0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAAB0aYi-aA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAAB0aYi-ZI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAAB0aYi-Zw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAAB0aYi-ZY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAAB0aYi-Z4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAAB0aYi-aI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAAB0aYi-Zo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAAB0aYi-Zs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Library installation errors - Sherin Suresh | Resolved by pinning compatible versions in requirements.txt
Sprint 1 | Day 3 | Slow data source connection due to firewall - Sherin Suresh | Coordinated with IT to whitelist required endpoints
Sprint 1 | Day 6 | Ambiguity in knowledge graph schema - Sherin Suresh | Held design review; finalized schema with mentor
Sprint 2 | Day 8 | LLM API rate limits slowing NER - Sherin Suresh, Rishabh Patel, Prem T Chavan | Team implemented batching and exponential backoff strategy
Sprint 2 | Day 10 | Neo4j connection issues in dev env - Sherin Suresh, Rishabh Patel, Prem T Chavan | Team switched to local Neo4j Desktop instance
Sprint 2 | Day 12 | Graph validation: missing relationships - Sherin Suresh, Rishabh Patel, Prem T Chavan | Team re-ran extraction pipeline with refined LLM prompts
Sprint 3 | Day 16 | Pinecone index config errors - Sherin Suresh, Rishabh Patel, Prem T Chavan | Team reconfigured index dimensions and tested with sample
Sprint 3 | Day 20 | RAG pipeline low accuracy - Sherin Suresh, Rishabh Patel, Prem T Chavan | Team tuned chunk size and overlap; improved prompt templates
Sprint 4 | Day 24 | Dashboard slow with large graph - Sherin Suresh, Rishabh Patel, Prem T Chavan | Team added pagination and lazy-loading to visualization
Sprint 4 | Day 28 | API errors: FastAPI and Neo4j - Sherin Suresh, Rishabh Patel, Prem T Chavan | Fixed async query handling; added connection pooling as a team
Sprint 4 | Day 32 | Deployment failing on cloud - Sherin Suresh, Rishabh Patel, Prem T Chavan | Team updated Docker config and added secrets management
Sprint 4 | Day 36 | Documentation incomplete - Sherin Suresh, Rishabh Patel, Prem T Chavan | All 3 members contributed; documentation completed by

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-02-13 | Sherin Suresh | Daily schema validation checks | Skipping code reviews under time pressure | Documenting all pipeline decisions | All 6 tasks completed. Ingestion pipeline and schema validated
2 | Sprint 2 | 2026-02-14 | 2026-02-27 | Sherin Suresh, Rishabh Patel, Prem T Chavan | Regular Neo4j graph integrity checks as a team | Delaying Neo4j commits to end of sprint | Team pair debugging NER and extraction issues | All 6 tasks completed by active team. Entities extracted and stored in Neo4j; graph validated.
3 | Sprint 3 | 2026-02-28 | 2026-03-13 | Sherin Suresh, Rishabh Patel, Prem T Chavan | Early embedding benchmarking before integration | Rushing RAG prompt design without team review | Team semantic search testing and collaboration | All 6 tasks completed by active team. Semantic search and RAG pipeline functional and optimized
4 | Sprint 4 | 2026-03-14 | 2026-03-26 | Sherin Suresh, Rishabh Patel, Prem T Chavan | CI/CD pipeline and deployment setup early as a team | Late-stage environment variable configuration | Cross-team API review and debugging sessions | All 6 tasks completed by active team. Dashboard deployed; documentation finalized
5 | All Sprints | 2026-02-02 | 2026-03-26 | Madhuri, Siri | Active participation and task ownership in future projects | Non-participation in coding, testing, and collaboration tasks | Attending stand-up meetings (if applicable) | Madhuri and Siri were listed as team members but did not contribute to any tasks across all 4 milestones (0 hours logged). No deliverables completed
6
7